## MS_NMP_Android
Release Number | Epic Id | Epic Name | Story Id | Story Name | Story DOD Sprint | Epic DOD Sprint
| E-06180 | [Android SDK 4.0] HLS Discontinuity |  |  |  | 2015-50 (1)
|  |  | B-22349 | [Android SDK 4.0] HLS Discontinuity | 2015-50 (1)
| E-06196 | [Android SDK 4.0] HLS / Live Time Shifting |  |  |  | 2015-50 (1)
|  |  | B-22334 | [Android SDK 4.0] Live Time Shifting / Allow time shift functionality | 2015-50 (1)
|  |  | B-28031 | [Android SDK 4.0] Live Time Shifting / Progress Bar | 2015-50 (1)
| E-07282 | [Android SDK 4.0] RTP |  |  |  | 2015-50 (1)
|  |  | B-28378 | [Android SDK 4.0] Integrate RTP Source into SDK build - Clear | 2015-50 (1)
|  |  | B-28379 | Update Ref App to demonstrate RTP stream playback | 2015-50 (1)
|  |  | B-29247 | [Android SDK 4.0] Integrate RTP Source into SDK build - Encrypted | 2015-50 (1)
| E-08121 | [Android SDK 4.0] In house device and platform test to replace Wicresoft |  |  |  | 2015-50 (1)
|  |  | B-34431 | [Android SDK 4.0] Documentation of In-House Platform Test Solution | 2015-50 (1)
|  |  | B-36699 | [Android SDK 4,0] Enable SDK 4 Test Harness to use In-House Platform Test Solution | 2015-50 (1)
|  |  | B-36700 | [Android HTML 4.0] Enable HTML 4 Test Harness to use In-House Platform Test Solution | 2015-50 (1)
| E-06179 | [Android SDK 4.0] HLS Byte-Range Access |  |  |  | 2015-52 (2)
|  |  | B-22326 | [Android SDK 4.0] HLS Byte Range | 2015-52 (2)
| E-06204 | [Android SDK 4.0] HLS Compressed Playlists |  |  |  | 2015-52 (2)
|  |  | B-22331 | [Android SDK 4.0] HLS Compressed Playlist | 2015-52 (2)
| E-06785 | [Android HTML 4.0] Download to Go |  |  |  | 2015-52 (2)
|  |  | B-25241 | [Android HTML 4.0] Download to Go / Integrate Download 2 go | 2015-52 (2)
|  |  | B-27526 | [Android HTML 4.0] Download to Go / Storage availability API for D2GO | 2015-52 (2)
| E-06181 | [Android SDK 4.0] ID3 Demuxing |  |  |  | 2016-01 (3)
|  |  | B-22332 | [Android SDK 4.0] ID3 Demuxing | 2016-01 (3)
| E-06202 | [Android SDK 4.0] PRM / Key Rotation (Sunrise) |  |  |  | 2016-01 (3)
|  |  | B-32588 | [Android SDK 4.0] PRM / Key Rotation (Sunrise) / Impact Story | 2016-01 (3)
| E-08093 | [Android SDK 4.0] Humax H1 HW decoders integration |  |  |  | 2016-01 (3)
|  |  | B-34426 | [Android SDK 4.0] [SAT>IP] Humax H1 HW decoders integration | 2015-52 (2)
|  |  | B-36694 | [Android SDK 4.0] [SAT>IP] Dynamic loads library. | 2016-01 (3)
| E-08260 | [Android HTML 4.0] Device Based Bit Rate Adaptation |  |  |  | 2016-01 (3)
|  |  | B-33606 | [Android HTML 4.0] Device Performance Based Bit Rate Adaptation / Open up APIs from SDK | 2016-01 (3)
| E-06192 | [Android SDK 4.0] HLS V.4 Multi-audio |  |  |  | 2016-03 (4)
|  |  | B-32581 | [Android SDK 4.0] HLS V.4 Multi-audio Validation | 2016-03 (4)
| E-08033 | [Android SDK NEX] - Support for Android M 6.0 API's |  |  |  | 2016-03 (4)
|  |  | B-32504 | [Android SDK NEX] Android M / SDK 6.0 - ".so has text relocation" issue. | 2016-01 (3)
|  |  | B-31514 | [Android SDK NEX] Android M permission support. | 2016-03 (4)
| E-06203 | [Android SDK 4.0] HLS Program Date Time |  |  |  | 2016-05 (5)
|  |  | B-33483 | [Android SDK 4.0] HLS Program Date Time / Fire event when reading new segment | 2016-05 (5)
|  |  | B-33484 | [Android SDK 4.0] HLS Program Date Time / Expose program date time | 2016-05 (5)
|  |  | B-33485 | [Android SDK 4.0] HLS / Current Program Date Time | 2016-05 (5)
| E-08034 | [Android SDK 4.0] - Support for Android M 6.0 API's |  |  |  | 2016-05 (5)
|  |  | B-32503 | [Android SDK 4.0] Android M / SDK 6.0 - ".so has text relocation" issue. | 2016-05 (5)
|  |  | B-36666 | [Android SDK 4.0] Android M permission support. | 2016-05 (5)
| E-08092 | [Android SDK 4.0] Single PAK Integration |  |  |  | 2016-05 (5)
|  |  | B-36698 | Integrate single PAK | 2016-05 (5)
| E-08125 | [Android SDK 4.0] Packager & Documentation refactor for Android - new process |  |  |  | 2016-07 (6)
|  |  | B-34427 | [Android SDK 4.0] Packager & Documentation refactor for Android - new process | 2016-07 (6)
| E-08259 | [Android HTML 4.0] Device Calibration |  |  |  | 2016-07 (6)
|  |  | B-33603 | [Android HTML 4.0] Device Bitrate Calibration/Configuration / Open up API's from SDK | 2016-07 (6)
| E-08337 | [Android HTML 4.0] HLS / Live Time Shifting |  |  |  | 2016-07 (6)
|  |  | B-34587 | [Android HTML 4.0] HLS / Live Time Shifting / Provide functionality on HTML Control Bar | 2016-07 (6)
| E-08441 | [Android HTML 4.0] - Support for Android M 6.0 API's |  |  |  | 2016-07 (6)
|  |  | B-33306 | [Android HTML 4.0] Android M permission support. | 2016-07 (6)
| E-08094 | [Android SDK NEX] Single PAK Integration |  |  |  | Not Planned
| E-08097 | [Android SDK 4.0] Player statistics |  |  |  | not planned
|  |  | B-33546 | [Android SDK 4.0] Player Statistics - Validation Playback statistics | 2015-50 (1)
|  |  | B-32618 | [Android SDK 4.0] Player Statistics - Network errors - HTTP error + event | 2016-03 (4)
|  |  | B-32623 | [Android SDK 4.0] Player Statistics - Playback - Stream error + event | 2016-03 (4)
|  |  | B-33541 | [Android SDK 4.0] Player Statistics - Network / Content Server - IP address after redirect | not planned
| E-08171 | [Android SDK 4.0][PR][5.4] - customer PR/Issues |  |  |  | Not Planned
| E-08172 | [Android SDK 4.0][PR][5.4] - non-customer PR/Issues |  |  |  | Not Planned
| E-08251 | [Android SDK 4.0] Android 3x -> Android 4x Migration Guide |  |  |  | Not Planned
| E-08252 | [Android HTML 4.0] Player Statistics |  |  |  | not planned
|  |  | B-32617 | [Android HTML 4.0] Player Statistics - Playback - Load event | 2016-03 (4)
|  |  | B-32624 | [Android HTML 4.0] Player Statistics - Playback - Current rendering bitrate + event | 2016-03 (4)
|  |  | B-32625 | [Android HTML 4.0] Player Statistics - Playback - Play state + event | 2016-03 (4)
|  |  | B-32634 | [Android HTML 4.0] Player Statistics - Playback - End state + event | 2016-03 (4)
|  |  | B-32636 | [Android HTML 4.0] Player Statistics - Playback - Buffering state + event | 2016-03 (4)
|  |  | B-32638 | [Android HTML 4.0] Player Statistics - Rendering / Video Rendering - Nominal FPS | 2016-03 (4)
|  |  | B-33540 | [Android HTML 4.0] Player Statistics - Playback - Stream error + event | 2016-05 (5)
|  |  | B-33543 | [Android HTML 4.0] Player Statistics - Network errors - Network error + event | 2016-05 (5)
|  |  | B-32621 | [Android HTML 4.0] Player Statistics - Network / Content Server - IP address after redirect | not planned
|  |  | B-33539 | [Android HTML 4.0] Player Statistics - Playback - Resume event | not planned
| E-08343 | [Android HTML 4.0][PR][5.4] - customer PR/Issues |  |  |  | Not Planned
| E-08344 | [Android HTML 4.0][PR][5.4] - non-customer PR/Issues |  |  |  | Not Planned
| E-08475 | [Handheld Android] Customer Integration, Maintenance and Support - PSI 2016.3 (SP5.4) |  |  |  | Not Planned
| E-08478 | [Handheld Android] Safe & PI Support - PSI 2016.3 (SP5.4) |  |  |  | Not Planned
| E-08488 | [Android] Team Specific, Code Improvements, Refactor & Training / Secure Player 5.4 |  |  |  | Not Planned
| E-08598 | [Android SDK Native][PR][5.4] customer PR/Issues |  |  |  | Not Planned
| E-08599 | [Android SDK Native][PR][5.4] non-customer PR/Issues |  |  |  | Not Planned
| E-08600 | [Android HTML Native][PR][5.4] customer PR/Issues |  |  |  | Not Planned
| E-08601 | [Android HTML Native][PR][5.4] non-customer PR/Issues |  |  |  | Not Planned
| E-08602 | [Android SDK NEX][PR][5.4] Customer PR/Issues |  |  |  | Not Planned